## Read me
Agentic SDLC: execution plan and tracker
v1 draft · Fri 23 Oct 2026 · for the biweekly review on Mon 26 Oct 2026 · owner: Amar Kumar (transformation lead)
What this is | The execution plan for the Agentic SDLC program: major areas, actions with sub-steps, measurable outputs, current status, dates, owners and the support each action needs. The plan page (index.html) explains the why; this file tracks the how and when.
Sheets | Summary: status by area. Plan: the tracker. Timeline: weekly view built from the Plan dates. KPIs: baselines and targets. Milestones: key dates and autonomy stages. Decisions: what we need from leadership. Task force: roles. Agent framework: the agents and what they merge. Risks. Evidence: industry practice with sources.
Weekly update | Every Friday by 17:00 the action owner updates Plan columns F (current status), G (status) and H (RAG). Dates change only with a decision at the biweekly review; note the reason in Remarks. IDs never change.
Status values | Not started · In progress · Ongoing · Done · Blocked.
RAG | Green: on track. Amber: at risk; the recovery step is in Remarks. Red: will miss its date without a decision; raise it at the next review.
Cell colours | Yellow fill: still to fill in (names, baselines). Blue numbers on the KPIs sheet: targets you can change. Black numbers: formulas; do not type over them. Green numbers: links to another sheet.
Sources | Targets 27/48 → 40/48 repos by November → 48/48 by January, the 1.3x multiple against a 10x aspiration, the single pilot team, the agent framework from December and the autonomy stages come from the company strategy document as discussed on the call with the program sponsor on Fri 23 Oct 2026. Everything else marked 'Proposed' is a recommendation to confirm on Mon 26 Oct.
Assumptions | Biweekly reviews with the executive sponsor every other Monday from Mon 26 Oct 2026. Task force in place by Mon 2 Nov 2026. Low capacity from Mon 21 Dec 2026 to Fri 1 Jan 2027. Diwali week in November may move the Mon 9 Nov review. All weekdays were checked against the calendar.
Related files | In the prd-to-pr-rule-skills repo: docs/adoption/index.html (plan page), docs/adoption/vision.md (source vision), docs/adoption/starter-kit/ (reference hooks, skills, subagents, templates and eval harness), and plugins/ (the standard that ships to every machine).

## Summary
Status by area
Every number on this sheet is a formula over the Plan sheet.
Area | Actions | Done | In progress | Ongoing | Not started | Blocked | Amber | Red | % done | Next open finish date
1. Program and task force | 9 | 0 | 4 | 0 | 5 | 0 | 2 | 0 | 0% | 2026-10-26
2. Measurement and baseline | 8 | 0 | 0 | 0 | 8 | 0 | 2 | 0 | 0% | 2026-11-06
3. Standardize repositories | 7 | 0 | 1 | 0 | 6 | 0 | 1 | 0 | 0% | 2026-11-06
4. Agent framework | 8 | 0 | 2 | 0 | 6 | 0 | 0 | 0 | 0% | 2026-11-06
5. Agentic SDLC workflow | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0% | 2026-11-06
6. Product builder | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0% | 2027-01-29
7. Security and operations | 5 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0% | 2026-11-27
8. Scale and ROI | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0% | 2027-08-27
All areas | 54 | 0 | 7 | 0 | 47 | 0 | 6 | 0 | 0% | 2026-10-26
This week
Open actions due in the next 14 days | 11
Open actions past their finish date | 0
Repos meeting the standard: baseline | 27
Repos meeting the standard: target Mon 30 Nov 2026 | 40
Repos meeting the standard: target Fri 29 Jan 2027 | 48
Next biweekly review | 2026-10-26
Formulas:
Next open finish date = IF(MINIFS(Plan!$J2:J400,Plan!$B2:B400,[Area],Plan!$G2:G400,"<>Done")=0,"",MINIFS(Plan!$J2:J400,Plan!$B2:B400,[Area],Plan!$G2:G400,"<>Done"))

## Plan
ID | Area | Action | Sub-steps | Measurable output (done when) | Current status (23 Oct 2026) | Status | RAG | Start | Planned finish | Owner | Support needed | Depends on | Stage | Remarks
1.1 | 1. Program and task force | Review plan v1 at the biweekly review | Walk through this tracker and the plan page; confirm targets (40/48 repos by 30 Nov, 48/48 by 29 Jan, framework v1 by 18 Dec); take decisions D1–D5; log changes. | Plan v1 accepted, or a dated change list; decisions recorded on the Decisions sheet. | Draft ready Fri 23 Oct; sponsor review over the weekend. | In progress | Green | 2026-10-23 | 2026-10-26 | Amar (lead) | Sponsor review before Monday; 30 minutes in the executive sponsor's review. |  | Program | Final version on Monday morning; share the draft earlier if asked.
1.2 | 1. Program and task force | Form the task force | Agree roles and allocation (Task force sheet); nominations from the engineering people leads; the executive sponsor approves; add members to the 11:00 meeting. | 6–7 named members, at least 50% allocated from Mon 2 Nov 2026 to Fri 29 Jan 2027, approved by the executive sponsor. | People leads agreed to provide people; names not confirmed. | In progress | Amber | 2026-10-26 | 2026-10-28 | Program sponsor | Nominations: engineering people leads. Approval: executive sponsor. | 1.1 | Program
1.3 | 1. Program and task force | Kick off the task force | Walk through the plan, the roles, the standard and the starter kit; every member takes first-week actions. | Kickoff held; every member owns at least one action in this tracker. | Not scheduled. | Not started | Green | 2026-10-29 | 2026-10-29 | Amar (lead) | Task force members. | 1.2 | Program
1.4 | 1. Program and task force | Run the program cadence | Daily 11:00 task-force stand-up; Friday demo; biweekly review with the executive sponsor; this tracker as the single source of truth, updated every Friday; decision and risk logs. | Cadence running from Thu 29 Oct; tracker updated every Friday by 17:00; every review starts from the tracker. | 11:00 meeting and biweekly review already exist. | Not started | Green | 2026-10-29 | 2027-10-29 | Amar (lead) | Members join the 11:00 meeting. | 1.3 | Program | Ongoing for the whole program.
1.5 | 1. Program and task force | Inventory and consolidate existing agent efforts | List every agent, skill, prompt library and bot built across teams, including the security, operations and requirement-analysis agents; record owner, purpose, users and tech; decide merge, keep or retire; invite owners to contribute through the framework. | Inventory with a decision for every item; no new standalone agents outside the framework after Fri 6 Nov. | Several teams have built agents on their own. | Not started | Amber | 2026-10-26 | 2026-11-06 | Amar (lead) | Team leads share what exists; The executive sponsor backs the one-framework rule (D3). |  | Program
1.6 | 1. Program and task force | Lead focus and working arrangement | Pause other work (for example Kompactor) until Fri 29 Jan 2027; spend 2–3 days a week on site with the sponsor during November. | Lead's time fully on this program; on-site days in the calendar. | Agreed in principle on the 23 Oct call. | In progress | Green | 2026-10-26 | 2026-10-30 | Amar (lead) | Sponsor; executive sponsor informed. |  | Program | Requested by the executive sponsor.
1.7 | 1. Program and task force | Industry evidence pack | Condense the company research already in this repo (docs/research.md: 29 sourced cases including Stripe, Spotify, Ramp, Uber and Airbnb) and vendor practice (Anthropic, OpenAI, Google) on skills, plugins and agents into one page with sources. | One-page evidence pack with cited sources, presented at the Mon 9 Nov review. | Research done (docs/research.md, companies page); key facts on the Evidence sheet. | In progress | Green | 2026-10-26 | 2026-11-06 | Amar (lead) |  |  | Program | Use it wherever the plan differs from a stated preference.
1.8 | 1. Program and task force | Align the strategy document | Answer the open review comments; link this tracker from the path-forward section; keep one set of targets across the document, the plan page and this tracker. | Comments resolved; document, page and tracker show the same targets and dates. | Comments open on the strategy document. | Not started | Green | 2026-10-26 | 2026-10-28 | Amar (lead) |  | 1.1 | Program
1.9 | 1. Program and task force | Engineering-wide communication | Announce the program, the standard and how to contribute; monthly showcase of the multi-agent lifecycle on a real change. | Announcement sent by Fri 6 Nov; first showcase Fri 18 Dec; monthly after that. | Not started. | Not started | Green | 2026-11-02 | 2026-12-18 | Program sponsor | Lead prepares the content. | 1.1 | Program
2.1 | 2. Measurement and baseline | Lock the baseline from internal analytics | Pull May–Oct 2026 per team: AI code share, change lead time (requirement to PR), epic lead time, PR throughput and success, defect resolution time, adoption scorecard, the 1.3x multiple; write definitions v1. | Baseline values entered on the KPIs sheet; definitions v1 signed off by the sponsor. | Numbers exist in internal analytics at pod level; definitions not locked. | Not started | Amber | 2026-10-26 | 2026-11-06 | Measurement analyst (TF) | Access to the analytics dashboards and data (D9). | 1.2 | Measure
2.2 | 2. Measurement and baseline | Measure AI code share in production | Agree the method: lines in AI-authored commits and PRs merged to main (Claude Code commit attribution plus OpenTelemetry) divided by all merged lines; keep attribution on through managed settings; dashboard by repo, team and month. | Dashboard live with weekly refresh; method written down; baseline recorded. | Named as the top company metric; production-level method not agreed. | Not started | Amber | 2026-11-02 | 2026-11-20 | Measurement analyst (TF) | Platform team for managed settings; analytics team for the dashboard. | 2.1, 7.2 | Measure
2.3 | 2. Measurement and baseline | Feature-level flow records for the pilot team | Adopt the feature-record schema (starter kit); join tracker, GitHub, deploy and telemetry data; per feature: request, intent, PR, production, impact. | 100% of the pilot team's features have a record from Tue 1 Dec 2026. | Epic lead time is measured at pod level only. | Not started | Green | 2026-11-02 | 2026-11-27 | Measurement analyst (TF) | Jira and GitHub admin access. | 2.1 | Measure | Replaces pod-level epic lead time.
2.4 | 2. Measurement and baseline | Scale feature-level records | Extend the records to each onboarded team; flag whether each change went through the standard workflow. | 4–5 backend teams covered by Fri 29 Jan 2027; all teams by Fri 30 Apr 2027. | Not started. | Not started | Green | 2027-01-04 | 2027-04-30 | Measurement analyst (TF) |  | 2.3 | Measure
2.5 | 2. Measurement and baseline | Claude Code telemetry for every builder | OpenTelemetry export with team tags through managed settings; join to the feature records; cost per team and per change. | At least 90% of sessions tagged by team; cost per successful change reported monthly. | Not confirmed whether telemetry is exported today. | Not started | Green | 2026-11-02 | 2026-11-13 | Platform/DevEx (TF) | IT for managed settings; observability team for the collector. | 7.2 | Measure
2.6 | 2. Measurement and baseline | Effort-distribution baseline | Classify the last two quarters of work into feature, defect, maintenance, risk reduction, tech debt and operational support with Claude; audit 40 rows by hand. | Shares per team; audit agreement at least 85%. | Not started. | Not started | Green | 2026-11-02 | 2026-11-13 | Measurement analyst (TF) |  | 2.1 | Measure
2.7 | 2. Measurement and baseline | Monthly gap report and scorecard | 0–10 per pillar with evidence; KPI trend against baseline; RAG per wave; the three decisions leadership needs. Claude drafts, owner reviews. | First report Fri 4 Dec 2026, then the first Friday of each month (Fri 8 Jan in January). | Gap assessment exists in the strategy document. | Not started | Green | 2026-12-04 | 2027-10-29 | Measurement analyst (TF) |  | 2.1 | Measure | Ongoing.
2.8 | 2. Measurement and baseline | Adoption hygiene | Named list of inactive builders with reasons; enablement for each; stop presenting adoption as the growth metric. | At least 95% of builders active weekly, or a named exception. | Adoption is high; exceptions not tracked by name. | Not started | Green | 2026-11-02 | 2026-11-27 | Platform/DevEx (TF) | Engineering managers. |  | Stage 1
3.1 | 3. Standardize repositories | Publish standard v2 | CLAUDE.md template, shared rules, make build/lint/test/verify, known traps, must-not-change rules; review with the 4–5 backend team leads. | Standard v2 published and approved by the backend team leads. | A standard exists; 27 of 48 repos meet it. | In progress | Green | 2026-10-26 | 2026-11-06 | Amar (lead) | Backend team leads review. |  | Stage 4
3.2 | 3. Standardize repositories | Automate the repo scorecard | CI check that scores each repo: CLAUDE.md sections, rules, make targets, guard hooks, frozen-test list, CODEOWNERS on guardrail files; weekly dashboard. | All 48 repos scored automatically every week. | Compliance counted by hand (27/48). | Not started | Green | 2026-11-02 | 2026-11-13 | Standardization squad (TF) |  | 3.1 | Stage 4
3.3 | 3. Standardize repositories | Rollout wave 1: 27 to 40 of 48 repos | Assign the 13 repos to the squad; draft CLAUDE.md with Claude (playbook R1); owning team reviews; merge; scorecard green. | 40 of 48 repos green on the scorecard. | 27 of 48. | Not started | Amber | 2026-11-02 | 2026-11-30 | Standardization squad (TF) | Each owning team: one review slot of about an hour per repo. | 3.1, 3.2 | Stage 4 | Target from the company plan.
3.4 | 3. Standardize repositories | Rollout wave 2: 40 to 48 of 48 repos | Same method for the last 8 repos; fix repos that dropped below the standard. | 48 of 48 repos green on the scorecard. | Not started. | Not started | Green | 2026-12-01 | 2027-01-29 | Standardization squad (TF) | Owning teams review. | 3.3 | Stage 4 | Target from the company plan.
3.5 | 3. Standardize repositories | Guardrails in every repo | Guard hooks, permission deny rules, frozen-test list and CODEOWNERS from the starter kit; hook self-test in CI; critical repos first. | Critical repos by Fri 18 Dec 2026; all 48 by Fri 29 Jan 2027. | sdlc-core hooks (shell, edit, PR and stop-verify guards) reach every machine through managed settings; the starter kit adds frozen-test and production-boundary guards to fold in. | Not started | Green | 2026-11-16 | 2027-01-29 | Standardization squad (TF) | Security champion reviews. | 3.1 | Stage 4
3.6 | 3. Standardize repositories | Policy packs v1 | Security, testing, API and logging/PII packs with rule IDs, drafted from recurring review comments (playbook R4). | Four packs published; reviewer agents cite rule IDs in findings. | Starter security pack exists in the kit. | Not started | Green | 2026-11-16 | 2026-12-11 | Security champion (TF) | Lead co-writes. | 3.1 | Stage 4
3.7 | 3. Standardize repositories | Required quality gates on every repo | make verify, the artifact check and the frozen-test check as required CI checks; gate pass rate per repo on the dashboard. | Required on 48 of 48 repos; pass rate visible per repo. | Not started. | Not started | Green | 2027-01-04 | 2027-02-26 | Standardization squad (TF) | Repo admins for branch protection. | 3.4 | Stage 4
4.1 | 4. Agent framework | Framework charter | One plugin as the unit of distribution: skills for workflow steps, subagents for specialists, hooks for guardrails, MCP connectors (Jira, GitHub, observability) and evals; naming, versioning, contribution and review rules; agent registry. | Charter approved at the Mon 9 Nov review, including decision D4 (skills-first, packaged as plugins). | This repo already ships the standard as a marketplace: sdlc-core (11 skills, 5 subagents, guard hooks, 5 eval cases), sdlc-connectors and stack plugins, enabled by managed settings. The charter makes it the one framework. | In progress | Green | 2026-10-26 | 2026-11-06 | Amar (lead) | Executive sponsor decision D4. | 1.5 | Stage 5
4.2 | 4. Agent framework | Internal plugin marketplace and framework CI | Framework repository; versioned releases; claude plugin validate --strict and the eval self-test as required checks; one-command install for every builder. | Marketplace live; plugin installs in one command; CI blocks broken releases. | In place in this repo: marketplace, managed settings with auto-update, strict validation in CI. Remaining: confirm every builder receives it; make the eval self-test a required check. | In progress | Green | 2026-11-09 | 2026-11-20 | Framework engineers (TF) | GitHub org admin for the marketplace repository. | 4.1 | Stage 4
4.3 | 4. Agent framework | Skill-launched UI spike | A skill that renders a change's intent, plan, evidence and review as an HTML page and opens it; decide whether anything richer is needed. | Demo at the Mon 23 Nov review, with a written recommendation. | Not started. | Not started | Green | 2026-11-09 | 2026-11-20 | Framework engineers (TF) |  | 4.1 | Stage 5 | Answers the executive sponsor's question on whether skills can launch a UI.
4.4 | 4. Agent framework | Framework v0.5: plan-and-build agents | Start from sdlc-core's prd-review, spec-write, plan, build and verify skills and its prd-analyst, repo-investigator, builder and qa-verifier agents; merge the existing requirement-analysis agent into prd-review; pilot team uses it daily. | v0.5 released and in daily use by the pilot team. | The skills and agents exist in sdlc-core; the pilot team does not use them daily yet. | Not started | Green | 2026-11-09 | 2026-11-27 | Framework engineers (TF) | Owner of the requirement-analysis agent. | 4.2 | Stage 5
4.5 | 4. Agent framework | Framework v1.0: full build-and-test lifecycle | Add architecture, security (merge the security team's agent) and test agents, plus release-manifest and incident-to-intent skills; feedback loop from mistakes to known traps and eval cases. | v1.0 released; at least 15 eval cases passing at 85% or better. | Not in sdlc-core yet: architecture and security reviewer agents, release manifest, incident-to-intent. Drafts are in docs/adoption/starter-kit. | Not started | Green | 2026-11-30 | 2026-12-18 | Framework engineers (TF) | Security champion. | 4.4 | Stage 5 | Company plan: agents from December.
4.6 | 4. Agent framework | Agent eval suite in CI | Seed cases from historical PRs (playbook E1); run on every framework change and weekly; publish the pass rate. | 15 cases by Fri 18 Dec; 30 by Fri 26 Feb 2027; pass rate of at least 85% enforced. | sdlc-core has 5 plugin-eval cases with a baseline arm (make evals); the starter kit adds a claude -p harness and EVAL-0001. | Not started | Green | 2026-11-23 | 2027-02-26 | Framework engineers (TF) |  | 4.2 | Stage 5
4.7 | 4. Agent framework | Continuous improvement loop | Every repeated agent mistake becomes a known trap and an eval case within 5 working days; weekly framework release notes. | Loop running; repeat-mistake count falls month on month. | Not started. | Not started | Green | 2026-12-01 | 2027-10-29 | Framework engineers (TF) |  | 4.5 | Stage 5 | Ongoing.
4.8 | 4. Agent framework | Operations (SRE) diagnosis agent | Merge the operations team's agent into an Agent SDK service with read-only observability tools; L1–L2 on one service. | Design approved Fri 29 Jan 2027; L1–L2 live on one service by Fri 26 Mar 2027. | An operations agent exists, built separately. | Not started | Green | 2027-01-04 | 2027-03-26 | Ops/SRE champion (TF) | Observability team; owner of the existing agent. | 4.5 | Stage 5
5.1 | 5. Agentic SDLC workflow | Pilot readout | Retro with the current pilot team; numbers so far (change lead time, rework); what to keep, change or stop. | Readout presented at the Mon 9 Nov review. | Pilot running in one team. | Not started | Green | 2026-10-26 | 2026-11-06 | Pilot team lead | Lead facilitates. |  | Stage 5
5.2 | 5. Agentic SDLC workflow | Standard workflow v1 with phase gates | Intent, spec, plan, code, test, PR, release evidence; a gate per phase; tiered by change class (trivial, standard, significant, high-risk); templates from the starter kit. | Workflow v1 published and used by the pilot team. | Templates and skills ready in the kit. | Not started | Green | 2026-11-02 | 2026-11-20 | Amar (lead) | Pilot team. | 5.1 | Stage 5 | Built from the pilot's feedback.
5.3 | 5. Agentic SDLC workflow | Pilot team reaches autonomy stage 2 | Agent drafts the intent and the PR; a human reviews the PR. Track the share of changes through the workflow every week. | At least 80% of the pilot team's eligible changes through the workflow; change lead time down 30% against baseline. | Today: agent assists, human approves (stage 1). | Not started | Green | 2026-11-23 | 2026-12-18 | Pilot team lead | Framework v0.5 (4.4). | 4.4, 5.2 | Stage 5
5.4 | 5. Agentic SDLC workflow | Onboard the 4–5 backend teams | Two cohorts; repo standard first; workflow training with the framework; weekly retro per team. | Cohort 1 live by Fri 29 Jan; cohort 2 by Fri 26 Feb; at least 60% of eligible changes through the workflow by Fri 30 Apr 2027. | Teams not yet named (D7). | Not started | Green | 2027-01-04 | 2027-04-30 | Amar (lead) | Engineering managers of the backend teams. | 3.3, 5.3 | Stage 5
5.5 | 5. Agentic SDLC workflow | Automated gates in shadow, then retire human gates | Log the automated decision next to the human one for every PR; retire a human gate for the standard class only after 4 weeks at 90% agreement and no missed blocker. | Shadow log from Mon 1 Feb 2027; first human gate retired for the standard class by Fri 30 Apr 2027. | Not started. | Not started | Green | 2027-02-01 | 2027-04-30 | Amar (lead) | Executive sponsor decision D10 when the bar is met. | 3.7 | Stage 3
5.6 | 5. Agentic SDLC workflow | Multi-agent PR review in CI | anthropics/claude-code-action with the code-review plugin and our reviewer agents; findings carry severity, evidence, file:line and policy. | Running on all pilot and cohort repos; human review time per PR down 20%. | Workflow file ready in the kit. | Not started | Green | 2027-02-01 | 2027-02-26 | Framework engineers (TF) | Repo admins; Claude GitHub App installed. | 4.5 | Stage 5
5.7 | 5. Agentic SDLC workflow | Release agent up to staging | Build once, deploy to dev, QA and staging with short-lived scoped credentials; release manifest written by the agent; production stays behind a human or policy gate. | Release manifests for 100% of standard changes in onboarded teams. | Not started. | Not started | Green | 2027-03-01 | 2027-03-26 | Framework engineers (TF) | Platform and release teams. | 5.6, 7.1 | Stage 5
5.8 | 5. Agentic SDLC workflow | Autonomy stage 3 for the standard class | Agent self-verifies with evidence; humans review exceptions. | Pilot and cohort-1 teams by Fri 30 Apr 2027; at least 10 standard changes from requirement to production with one builder and automated controls, change failure rate no worse than baseline. | Not started. | Not started | Green | 2027-03-29 | 2027-04-30 | Amar (lead) |  | 5.5, 5.7 | Stage 3 | This is the Stage 3 (Empower) exit for one class.
6.1 | 6. Product builder | Product-builder role draft | Co-write with the pilot team: what builders own, what they stop doing, new paths for QA, PM and release specialists. | Draft reviewed by engineering leadership by Fri 29 Jan 2027. | Role described in the strategy document only. | Not started | Green | 2027-01-04 | 2027-01-29 | Program sponsor | HR partner; pilot team. | 5.3 | Stage 2
6.2 | 6. Product builder | One accountable builder per feature | In onboarded teams, one builder owns each feature from intent to release evidence; measure handoff depth per feature. | At least 70% of features in onboarded teams with handoff depth of 2 or less by Fri 30 Apr 2027. | Not started. | Not started | Green | 2027-02-01 | 2027-04-30 | Program sponsor | Engineering managers. | 2.4, 6.1 | Stage 2
6.3 | 6. Product builder | Team-level scorecards | Scorecards from the feature records for every onboarded team; no individual leaderboards. | Scorecards live for all onboarded teams. | Not started. | Not started | Green | 2027-03-01 | 2027-03-26 | Measurement analyst (TF) |  | 2.4 | Stage 2
6.4 | 6. Product builder | Builder training and certification | Curriculum delivered as skills plus live sessions; practical certification on a real change. | Pilot and cohorts certified by Fri 30 Apr 2027; 80% of builders by Fri 30 Jul 2027. | Not started. | Not started | Green | 2027-02-01 | 2027-07-30 | Amar (lead) | Engineering managers schedule time. | 4.5 | Stage 2
6.5 | 6. Product builder | Role in the career framework | Expectations, levels and review criteria for product builders. | Approved by HR and engineering leadership; used in the next review cycle. | Not started. | Not started | Green | 2027-05-03 | 2027-07-30 | Program sponsor | HR; Executive sponsor decision D12. | 6.1 | Stage 2
7.1 | 7. Security and operations | No production credentials for agents | Review how agent sessions authenticate; short-lived, environment-scoped credentials for dev, QA and staging; sandbox with a network allowlist. | Access review signed off; zero agent sessions with production credentials. | Not reviewed. | Not started | Amber | 2026-11-02 | 2026-11-27 | Security champion (TF) | Cloud and IAM team. |  | Stage 5
7.2 | 7. Security and operations | Managed settings for all builders | No bypass mode, secret deny rules, sandbox, telemetry, approved marketplaces only. | Deployed to 100% of builder machines. | policy/managed-settings.json in this repo sets deny rules, no bypass mode, strict marketplaces and auto-update; not yet deployed to every builder. | Not started | Green | 2026-11-09 | 2026-11-27 | Platform/DevEx (TF) | IT endpoint management. |  | Stage 1
7.3 | 7. Security and operations | Monthly failure review | Review recurring failures every month; convert each into a rule, test, hook or eval; track the conversion-to-control rate. | First review Fri 4 Dec 2026; conversion rate at least 80% by Fri 30 Apr 2027. | Listed as a must-fix in the gap assessment. | Not started | Green | 2026-12-04 | 2027-10-29 | Ops/SRE champion (TF) | Team leads bring their failures. |  | Stage 5 | Ongoing.
7.4 | 7. Security and operations | Incident to controls | Run /incident-to-intent for every incident: intent, frozen regression test, eval case, known trap and a proposed hook. | 100% of incidents in onboarded teams converted within 5 working days, from Mon 4 Jan 2027. | Skill ready in the kit. | Not started | Green | 2027-01-04 | 2027-10-29 | Ops/SRE champion (TF) | Incident owners. | 4.5 | Stage 5 | Ongoing.
7.5 | 7. Security and operations | Autonomy ladder policy | Allowed autonomy level per service and action; L4 runbooks approved by SRE; no L5 in the first year. | Policy approved (decision D11). | Not started. | Not started | Green | 2027-05-03 | 2027-05-28 | Ops/SRE champion (TF) | Head of SRE. | 4.8 | Stage 5
8.1 | 8. Scale and ROI | Scale the workflow to all teams | Cohorts of two teams per month; repo standard and training first; framework from the marketplace. | At least 70% of eligible changes through the workflow across engineering by Fri 29 Oct 2027. | Not started. | Not started | Green | 2027-05-03 | 2027-10-29 | Amar (lead) | Engineering managers. | 5.4 | Stage 5 | Company plan mentions 80% builders and 70% adoption; confirm.
8.2 | 8. Scale and ROI | SRE and incident agents at L1–L3 | Extend the diagnosis agent to onboarded services; high-confidence findings open a draft intent PR. | L1–L3 on onboarded services; on-call rates the hypothesis correct in at least 70% of diagnosed alerts. | Not started. | Not started | Green | 2027-06-07 | 2027-08-27 | Ops/SRE champion (TF) | On-call teams. | 4.8, 7.5 | Stage 5
8.3 | 8. Scale and ROI | ROI review on measured numbers | Fill the ROI formula with sourced inputs; sensitivity analysis; what cannot be attributed to the program. | ROI review presented to the executive sponsor. | Not started. | Not started | Green | 2027-10-18 | 2027-10-29 | Measurement analyst (TF) | Finance for program costs. | 2.7 | Program
8.4 | 8. Scale and ROI | 12-month readout and year-two plan | Re-rate the gap assessment with evidence; propose year-two scope. | Readout held Mon 1 Nov 2027. | Not started. | Not started | Green | 2027-10-18 | 2027-11-01 | Amar (lead) |  | 8.3 | Program
Note |  | Owners marked (TF) are task-force roles until names are confirmed (action 1.2). Overdue open actions turn the Planned finish date red.
Note on K11: Role until the task force names a person (action 1.2).
Note on K12: Role until the task force names a person (action 1.2).
Note on K13: Role until the task force names a person (action 1.2).
Note on K14: Role until the task force names a person (action 1.2).
Note on K15: Role until the task force names a person (action 1.2).
Note on K16: Role until the task force names a person (action 1.2).
Note on K17: Role until the task force names a person (action 1.2).
Note on K18: Role until the task force names a person (action 1.2).
Note on K20: Role until the task force names a person (action 1.2).
Note on K21: Role until the task force names a person (action 1.2).
Note on K22: Role until the task force names a person (action 1.2).
Note on K23: Role until the task force names a person (action 1.2).
Note on K24: Role until the task force names a person (action 1.2).
Note on K25: Role until the task force names a person (action 1.2).
Note on K27: Role until the task force names a person (action 1.2).
Note on K28: Role until the task force names a person (action 1.2).
Note on K29: Role until the task force names a person (action 1.2).
Note on K30: Role until the task force names a person (action 1.2).
Note on K31: Role until the task force names a person (action 1.2).
Note on K32: Role until the task force names a person (action 1.2).
Note on K33: Role until the task force names a person (action 1.2).
Note on K34: Role until the task force names a person (action 1.2).
Note on K36: Role until the task force names a person (action 1.2).
Note on K39: Role until the task force names a person (action 1.2).
Note on K40: Role until the task force names a person (action 1.2).
Note on K44: Role until the task force names a person (action 1.2).
Note on K47: Role until the task force names a person (action 1.2).
Note on K48: Role until the task force names a person (action 1.2).
Note on K49: Role until the task force names a person (action 1.2).
Note on K50: Role until the task force names a person (action 1.2).
Note on K51: Role until the task force names a person (action 1.2).
Note on K53: Role until the task force names a person (action 1.2).
Note on K54: Role until the task force names a person (action 1.2).

## Timeline
Timeline by week
Built from the Plan sheet's dates. Amber marks the finish week. |  |  |  | Oct 26 | Nov 26 |  |  |  | Dec 26 |  |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  | Apr 27 |  |  |  |  | May 27 |  |  |  | Jun 27 |  |  |  | Jul 27 |  |  |  |  | Aug 27 |  |  |  | Sep 27 |  |  |  |  | Oct 27 |  |  |  | Nov 27
 | time axis 2026-10-26 to 2027-11-01
ID | Action | Start | Finish | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30 | 2027-09-06 | 2027-09-13 | 2027-09-20 | 2027-09-27 | 2027-10-04 | 2027-10-11 | 2027-10-18 | 2027-10-25 | 2027-11-01
1.1 | Review plan v1 at the biweekly review | 2026-10-23 | 2026-10-26 | 2026-10-26: 2
1.2 | Form the task force | 2026-10-26 | 2026-10-28 | 2026-10-26: 2
1.3 | Kick off the task force | 2026-10-29 | 2026-10-29 | 2026-10-26: 2
1.4 | Run the program cadence | 2026-10-29 | 2027-10-29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
1.5 | Inventory and consolidate existing agent efforts | 2026-10-26 | 2026-11-06 | 2026-10-26: 1; 2026-11-02: 2
1.6 | Lead focus and working arrangement | 2026-10-26 | 2026-10-30 | 2026-10-26: 2
1.7 | Industry evidence pack | 2026-10-26 | 2026-11-06 | 2026-10-26: 1; 2026-11-02: 2
1.8 | Align the strategy document | 2026-10-26 | 2026-10-28 | 2026-10-26: 2
1.9 | Engineering-wide communication | 2026-11-02 | 2026-12-18 | 2026-11-02: 1; 2026-11-09: 1; 2026-11-16: 1; 2026-11-23: 1; 2026-11-30: 1; 2026-12-07: 1; 2026-12-14: 2
2.1 | Lock the baseline from internal analytics | 2026-10-26 | 2026-11-06 | 2026-10-26: 1; 2026-11-02: 2
2.2 | Measure AI code share in production | 2026-11-02 | 2026-11-20 | 2026-11-02: 1; 2026-11-09: 1; 2026-11-16: 2
2.3 | Feature-level flow records for the pilot team | 2026-11-02 | 2026-11-27 | 2026-11-02: 1; 2026-11-09: 1; 2026-11-16: 1; 2026-11-23: 2
2.4 | Scale feature-level records | 2027-01-04 | 2027-04-30 | 2027-01-04: 1; 2027-01-11: 1; 2027-01-18: 1; 2027-01-25: 1; 2027-02-01: 1; 2027-02-08: 1; 2027-02-15: 1; 2027-02-22: 1; 2027-03-01: 1; 2027-03-08: 1; 2027-03-15: 1; 2027-03-22: 1; 2027-03-29: 1; 2027-04-05: 1; 2027-04-12: 1; 2027-04-19: 1; 2027-04-26: 2
2.5 | Claude Code telemetry for every builder | 2026-11-02 | 2026-11-13 | 2026-11-02: 1; 2026-11-09: 2
2.6 | Effort-distribution baseline | 2026-11-02 | 2026-11-13 | 2026-11-02: 1; 2026-11-09: 2
2.7 | Monthly gap report and scorecard | 2026-12-04 | 2027-10-29 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
2.8 | Adoption hygiene | 2026-11-02 | 2026-11-27 | 2026-11-02: 1; 2026-11-09: 1; 2026-11-16: 1; 2026-11-23: 2
3.1 | Publish standard v2 | 2026-10-26 | 2026-11-06 | 2026-10-26: 1; 2026-11-02: 2
3.2 | Automate the repo scorecard | 2026-11-02 | 2026-11-13 | 2026-11-02: 1; 2026-11-09: 2
3.3 | Rollout wave 1: 27 to 40 of 48 repos | 2026-11-02 | 2026-11-30 | 2026-11-02: 1; 2026-11-09: 1; 2026-11-16: 1; 2026-11-23: 1; 2026-11-30: 2
3.4 | Rollout wave 2: 40 to 48 of 48 repos | 2026-12-01 | 2027-01-29 | 2026-11-30: 1; 2026-12-07: 1; 2026-12-14: 1; 2026-12-21: 1; 2026-12-28: 1; 2027-01-04: 1; 2027-01-11: 1; 2027-01-18: 1; 2027-01-25: 2
3.5 | Guardrails in every repo | 2026-11-16 | 2027-01-29 | 2026-11-16: 1; 2026-11-23: 1; 2026-11-30: 1; 2026-12-07: 1; 2026-12-14: 1; 2026-12-21: 1; 2026-12-28: 1; 2027-01-04: 1; 2027-01-11: 1; 2027-01-18: 1; 2027-01-25: 2
3.6 | Policy packs v1 | 2026-11-16 | 2026-12-11 | 2026-11-16: 1; 2026-11-23: 1; 2026-11-30: 1; 2026-12-07: 2
3.7 | Required quality gates on every repo | 2027-01-04 | 2027-02-26 | 2027-01-04: 1; 2027-01-11: 1; 2027-01-18: 1; 2027-01-25: 1; 2027-02-01: 1; 2027-02-08: 1; 2027-02-15: 1; 2027-02-22: 2
4.1 | Framework charter | 2026-10-26 | 2026-11-06 | 2026-10-26: 1; 2026-11-02: 2
4.2 | Internal plugin marketplace and framework CI | 2026-11-09 | 2026-11-20 | 2026-11-09: 1; 2026-11-16: 2
4.3 | Skill-launched UI spike | 2026-11-09 | 2026-11-20 | 2026-11-09: 1; 2026-11-16: 2
4.4 | Framework v0.5: plan-and-build agents | 2026-11-09 | 2026-11-27 | 2026-11-09: 1; 2026-11-16: 1; 2026-11-23: 2
4.5 | Framework v1.0: full build-and-test lifecycle | 2026-11-30 | 2026-12-18 | 2026-11-30: 1; 2026-12-07: 1; 2026-12-14: 2
4.6 | Agent eval suite in CI | 2026-11-23 | 2027-02-26 | 2026-11-23: 1; 2026-11-30: 1; 2026-12-07: 1; 2026-12-14: 1; 2026-12-21: 1; 2026-12-28: 1; 2027-01-04: 1; 2027-01-11: 1; 2027-01-18: 1; 2027-01-25: 1; 2027-02-01: 1; 2027-02-08: 1; 2027-02-15: 1; 2027-02-22: 2
4.7 | Continuous improvement loop | 2026-12-01 | 2027-10-29 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
4.8 | Operations (SRE) diagnosis agent | 2027-01-04 | 2027-03-26 | 2027-01-04: 1; 2027-01-11: 1; 2027-01-18: 1; 2027-01-25: 1; 2027-02-01: 1; 2027-02-08: 1; 2027-02-15: 1; 2027-02-22: 1; 2027-03-01: 1; 2027-03-08: 1; 2027-03-15: 1; 2027-03-22: 2
5.1 | Pilot readout | 2026-10-26 | 2026-11-06 | 2026-10-26: 1; 2026-11-02: 2
5.2 | Standard workflow v1 with phase gates | 2026-11-02 | 2026-11-20 | 2026-11-02: 1; 2026-11-09: 1; 2026-11-16: 2
5.3 | Pilot team reaches autonomy stage 2 | 2026-11-23 | 2026-12-18 | 2026-11-23: 1; 2026-11-30: 1; 2026-12-07: 1; 2026-12-14: 2
5.4 | Onboard the 4–5 backend teams | 2027-01-04 | 2027-04-30 | 2027-01-04: 1; 2027-01-11: 1; 2027-01-18: 1; 2027-01-25: 1; 2027-02-01: 1; 2027-02-08: 1; 2027-02-15: 1; 2027-02-22: 1; 2027-03-01: 1; 2027-03-08: 1; 2027-03-15: 1; 2027-03-22: 1; 2027-03-29: 1; 2027-04-05: 1; 2027-04-12: 1; 2027-04-19: 1; 2027-04-26: 2
5.5 | Automated gates in shadow, then retire human gates | 2027-02-01 | 2027-04-30 | 2027-02-01: 1; 2027-02-08: 1; 2027-02-15: 1; 2027-02-22: 1; 2027-03-01: 1; 2027-03-08: 1; 2027-03-15: 1; 2027-03-22: 1; 2027-03-29: 1; 2027-04-05: 1; 2027-04-12: 1; 2027-04-19: 1; 2027-04-26: 2
5.6 | Multi-agent PR review in CI | 2027-02-01 | 2027-02-26 | 2027-02-01: 1; 2027-02-08: 1; 2027-02-15: 1; 2027-02-22: 2
5.7 | Release agent up to staging | 2027-03-01 | 2027-03-26 | 2027-03-01: 1; 2027-03-08: 1; 2027-03-15: 1; 2027-03-22: 2
5.8 | Autonomy stage 3 for the standard class | 2027-03-29 | 2027-04-30 | 2027-03-29: 1; 2027-04-05: 1; 2027-04-12: 1; 2027-04-19: 1; 2027-04-26: 2
6.1 | Product-builder role draft | 2027-01-04 | 2027-01-29 | 2027-01-04: 1; 2027-01-11: 1; 2027-01-18: 1; 2027-01-25: 2
6.2 | One accountable builder per feature | 2027-02-01 | 2027-04-30 | 2027-02-01: 1; 2027-02-08: 1; 2027-02-15: 1; 2027-02-22: 1; 2027-03-01: 1; 2027-03-08: 1; 2027-03-15: 1; 2027-03-22: 1; 2027-03-29: 1; 2027-04-05: 1; 2027-04-12: 1; 2027-04-19: 1; 2027-04-26: 2
6.3 | Team-level scorecards | 2027-03-01 | 2027-03-26 | 2027-03-01: 1; 2027-03-08: 1; 2027-03-15: 1; 2027-03-22: 2
6.4 | Builder training and certification | 2027-02-01 | 2027-07-30 | 2027-02-01: 1; 2027-02-08: 1; 2027-02-15: 1; 2027-02-22: 1; 2027-03-01: 1; 2027-03-08: 1; 2027-03-15: 1; 2027-03-22: 1; 2027-03-29: 1; 2027-04-05: 1; 2027-04-12: 1; 2027-04-19: 1; 2027-04-26: 1; 2027-05-03: 1; 2027-05-10: 1; 2027-05-17: 1; 2027-05-24: 1; 2027-05-31: 1; 2027-06-07: 1; 2027-06-14: 1; 2027-06-21: 1; 2027-06-28: 1; 2027-07-05: 1; 2027-07-12: 1; 2027-07-19: 1; 2027-07-26: 2
6.5 | Role in the career framework | 2027-05-03 | 2027-07-30 | 2027-05-03: 1; 2027-05-10: 1; 2027-05-17: 1; 2027-05-24: 1; 2027-05-31: 1; 2027-06-07: 1; 2027-06-14: 1; 2027-06-21: 1; 2027-06-28: 1; 2027-07-05: 1; 2027-07-12: 1; 2027-07-19: 1; 2027-07-26: 2
7.1 | No production credentials for agents | 2026-11-02 | 2026-11-27 | 2026-11-02: 1; 2026-11-09: 1; 2026-11-16: 1; 2026-11-23: 2
7.2 | Managed settings for all builders | 2026-11-09 | 2026-11-27 | 2026-11-09: 1; 2026-11-16: 1; 2026-11-23: 2
7.3 | Monthly failure review | 2026-12-04 | 2027-10-29 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
7.4 | Incident to controls | 2027-01-04 | 2027-10-29 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
7.5 | Autonomy ladder policy | 2027-05-03 | 2027-05-28 | 2027-05-03: 1; 2027-05-10: 1; 2027-05-17: 1; 2027-05-24: 2
8.1 | Scale the workflow to all teams | 2027-05-03 | 2027-10-29 | 2027-05-03: 1; 2027-05-10: 1; 2027-05-17: 1; 2027-05-24: 1; 2027-05-31: 1; 2027-06-07: 1; 2027-06-14: 1; 2027-06-21: 1; 2027-06-28: 1; 2027-07-05: 1; 2027-07-12: 1; 2027-07-19: 1; 2027-07-26: 1; 2027-08-02: 1; 2027-08-09: 1; 2027-08-16: 1; 2027-08-23: 1; 2027-08-30: 1; 2027-09-06: 1; 2027-09-13: 1; 2027-09-20: 1; 2027-09-27: 1; 2027-10-04: 1; 2027-10-11: 1; 2027-10-18: 1; 2027-10-25: 2
8.2 | SRE and incident agents at L1–L3 | 2027-06-07 | 2027-08-27 | 2027-06-07: 1; 2027-06-14: 1; 2027-06-21: 1; 2027-06-28: 1; 2027-07-05: 1; 2027-07-12: 1; 2027-07-19: 1; 2027-07-26: 1; 2027-08-02: 1; 2027-08-09: 1; 2027-08-16: 1; 2027-08-23: 2
8.3 | ROI review on measured numbers | 2027-10-18 | 2027-10-29 | 2027-10-18: 1; 2027-10-25: 2
8.4 | 12-month readout and year-two plan | 2027-10-18 | 2027-11-01 | 2027-10-18: 1; 2027-10-25: 1; 2027-11-01: 2
Teal: action in progress that week. Amber: planned finish week. Amber header: the current week.

## KPIs
KPIs: baselines and targets
Blue cells are targets you can change. Yellow cells are baselines to fill from internal analytics (action 2.1). Black cells are formulas.
Absolute targets
KPI | Definition | Source | Unit | Better when | Baseline (Oct 2026) | Mon 30 Nov 2026 | Fri 29 Jan 2027 | Fri 30 Apr 2027 | Fri 29 Oct 2027 | Owner | Target status / note
Repos meeting the standard (of 48) | Repos green on the scorecard: CLAUDE.md, rules, make targets, guardrails. | Repo scorecard (3.2) | repos | Higher | 27 | 40 | 48 | 48 | 48 | Standardization squad (TF) | From the company plan.
Critical repos with guardrails | Share of critical repos with guard hooks, deny rules, frozen tests and CODEOWNERS. | Repo scorecard | % | Higher |  | 50% | 100% | 100% | 100% | Standardization squad (TF) | Proposed.
Pilot team: eligible changes through the workflow | Non-trivial changes that followed the artifact chain for their class. | Feature records (2.3) | % | Higher |  | 50% | 80% | 90% | 90% | Pilot team lead | Proposed.
Backend teams: eligible changes through the workflow | Same measure for the 4–5 onboarded backend teams. | Feature records (2.4) | % | Higher |  |  | 30% | 60% | 80% | Amar (lead) | Proposed.
Builders on the standard workflow | Builders with at least one change through the workflow in the month. | Feature records | % | Higher |  | 10% | 30% | 50% | 80% | Amar (lead) | Company plan mentions 80%; confirm.
Feature-level record coverage | Share of features with a complete record. | Feature records | % | Higher | 0% | 15% | 40% | 100% | 100% | Measurement analyst (TF) | Proposed.
Agent eval pass rate | Passed runs ÷ total runs on the eval suite. | evals/results | % | Higher |  |  | 85% | 90% | 90% | Framework engineers (TF) | Proposed.
Agent eval cases | Cases in the suite that pass --self-test. | evals/cases | cases | Higher | 1 | 5 | 20 | 30 | 60 | Framework engineers (TF) | Proposed. Baseline: EVAL-0001 in the starter kit.
Conversion-to-control rate | Recurring failures converted into a rule, test, hook or eval ÷ recurring failures reviewed. | Monthly failure review (7.3) | % | Higher |  |  | 50% | 80% | 90% | Ops/SRE champion (TF) | Proposed.
Agent sessions with production credentials | Count found in the access review. | Access review (7.1) | sessions | Lower |  | 0 | 0 | 0 | 0 | Security champion (TF) | Hard rule.
Repos in scope |  |  |  |  | 48
Repos meeting the standard, share of repos in scope |  |  |  |  | 56.25% | 83.33% | 100% | 100% | 100%
Relative targets: change against the baseline
Target = baseline × (1 + change) for relative KPIs, or baseline + change for points and multiples. Change inputs are in columns M–P. Fill the yellow baselines and the targets appear.
KPI | Definition | Source | Unit | Method | Baseline (Oct 2026) | Target 30 Nov 2026 | Target 29 Jan 2027 | Target 30 Apr 2027 | Target 29 Oct 2027 | Owner | Target status / note | Change by 30 Nov | Change by 29 Jan | Change by 30 Apr | Change by 29 Oct 27
AI code share in production | Lines in AI-authored commits merged to main ÷ all merged lines. | AI code share dashboard (2.2) | % | points | [5 empty] | Measurement analyst (TF) | Company's top metric. Proposed targets. | 0 | 10 | 20 | 30
Change lead time, requirement to PR (pilot team) | Median days from approved intent to PR opened. | Feature records | days | relative | [5 empty] | Pilot team lead | Proposed. | -15% | -30% | -50% | -60%
Feature lead time, request to production | Median days from request received to production (replaces pod-level epic lead time). | Feature records | days | relative | [5 empty] | Measurement analyst (TF) | Proposed. | 0% | -10% | -25% | -40%
Human review time per PR | Median reviewer hours per PR. | GitHub review events | hours | relative | [5 empty] | Amar (lead) | Proposed. | 0% | -20% | -35% | -50%
First-pass PR success | Share of PRs with green CI on the first push. | CI | % | points | [5 empty] | Standardization squad (TF) | Proposed. | 0 | 5 | 10 | 15
Escaped defects per month | Defects traced to a change within 30 days. | Tracker links | defects | relative | [5 empty] | Ops/SRE champion (TF) | No worse than baseline while speed rises. | 0% | 0% | -10% | -25%
Repeat preventable failures per quarter | Incidents or failures with a known earlier cause. | Monthly failure review | count | relative | [5 empty] | Ops/SRE champion (TF) | Proposed. | 0% | 0% | -15% | -30%
Productivity multiple (company measure) | As defined in the strategy document. | Strategy document | x | points | 1.3 | 1.3 | 1.5 | 2 | 3 | Amar (lead) | Baseline 1.3x from the strategy document; aspiration 10x. Targets proposed for onboarded teams. | 0 | 0.2 | 0.7 | 1.7
Note on F16: 48 repos in scope, from the company plan (23 Oct 2026 call).
Note on F29: From the company strategy document, as discussed on the 23 Oct 2026 call.

## Milestones
Milestones and autonomy stages
Gate reviews fall on the biweekly review after each wave ends.
Date | Milestone | Measure | Wave | Owner
2026-10-26 | Plan v1 reviewed with the executive sponsor | Decisions D1–D5 taken | W0 Mobilize | Amar (lead)
2026-10-28 | Task force approved | 6–7 named members, at least 50% allocated | W0 Mobilize | Program sponsor
2026-10-29 | Task force kickoff | Every member owns at least one action | W0 Mobilize | Amar (lead)
2026-11-06 | Baseline locked; standard v2; framework charter; pilot readout | KPIs sheet baselines filled; charter ready for D4 | W0 Mobilize | Amar (lead)
2026-11-09 | Gate review W0 | Charter approved; evidence pack presented | W0 Mobilize | Executive sponsor
2026-11-20 | AI code share dashboard; plugin marketplace; UI spike | Dashboard live; one-command install; spike demo ready | W1 Standardize and instrument | Measurement analyst (TF)
2026-11-27 | Framework v0.5 in daily use by the pilot team | Pilot team uses intent, planning and verifier agents | W1 Standardize and instrument | Framework engineers (TF)
2026-11-30 | 40 of 48 repos meet the standard | Scorecard | W1 Standardize and instrument | Standardization squad (TF)
2026-12-07 | Gate review W1 | 40/48; telemetry; access review signed off | W1 Standardize and instrument | Executive sponsor
2026-12-18 | Framework v1.0; pilot team at autonomy stage 2; first showcase | 15 eval cases at 85%+; 80% of pilot changes through the workflow | W2 Framework v1 and expansion | Framework engineers (TF)
2027-01-29 | 48 of 48 repos; backend cohort 1 live; role draft | Scorecard; feature records for 4–5 backend teams | W2 Framework v1 and expansion | Standardization squad (TF)
2027-02-01 | Gate review W2 | Shadow gates start | W2 Framework v1 and expansion | Executive sponsor
2027-02-26 | Backend cohort 2 live; required gates on 48/48; multi-agent PR review | 30 eval cases | W3 Automated gates and scale | Amar (lead)
2027-03-26 | Release agent up to staging; SRE agent L1–L2 on one service | Manifests for 100% of standard changes in onboarded teams | W3 Automated gates and scale | Framework engineers (TF)
2027-04-30 | First human gate retired; autonomy stage 3 for the standard class | 4 weeks at 90%+ agreement; 10+ changes with one builder and automated controls | W3 Automated gates and scale | Amar (lead)
2027-05-10 | Gate review W3 | Decision D10 on the production policy gate | W3 Automated gates and scale | Executive sponsor
2027-07-30 | 80% of builders certified; role in the career framework | Certification records; HR approval | W4 Scale and the builder role | Program sponsor
2027-08-27 | SRE and incident agents at L1–L3 on onboarded services | 70%+ correct hypotheses | W5 Close the loop | Ops/SRE champion (TF)
2027-10-29 | ROI review; 70% of eligible changes through the workflow | Sourced ROI with sensitivity analysis | W5 Close the loop | Measurement analyst (TF)
2027-11-01 | 12-month readout and year-two plan | Gap assessment re-rated with evidence | W5 Close the loop | Amar (lead)
Autonomy stages (from the company plan)
Stage | Agent does | Human does | Pilot team | Backend teams (4–5) | All teams
1 Foundation (today) | Assists with code | Writes intents and plans; approves everything | Today | Today | Today
2 | Drafts the intent and the PR | Reviews the PR | 2026-12-18 | 2027-02-26 | 2027-07-30
3 | Self-verifies with evidence | Reviews exceptions | 2027-04-30 | 2027-06-25 | 2027-10-29
4 | Fixes what production signals find and opens the PR (L3) | Final review | 2027-08-27 | Year two | Year two
5 | Remediates within guardrails (L4 named runbooks only) | Audits | Named runbooks after D11 | Year two | Not in year one
Stage dates are proposals for the Mon 26 Oct review.

## Decisions
Decisions needed from leadership
Bring the open ones to the biweekly review on the date shown.
ID | Decision | Recommendation | Needed by | Decided by | Status | Outcome
D1 | Approve plan v1: targets, dates and way of working | Approve, with changes logged. Keep the company targets (40/48 by 30 Nov, 48/48 by 29 Jan, framework from December). Adopt the artifact chain, tiered by change class, and the repo standard as the way of working. | 2026-10-26 | Executive sponsor | Open
D2 | Task force | 6–7 people at least 50% allocated from Mon 2 Nov to Fri 29 Jan, nominated by the engineering people leads (Task force sheet). | 2026-10-28 | Executive sponsor with the people leads | Open
D3 | One framework, run like production code | Every agent, skill and automation goes through the shared framework; owners of existing agents join as contributors; no new standalone agents after Fri 6 Nov. Framework changes go through PRs with code owners and must pass the eval suite. | 2026-10-26 | Executive sponsor | Open
D4 | Form of the framework | Skills-first, packaged as plugins from an internal marketplace. Add hooks where rules must be enforced, subagents for specialist reviews, MCP connectors for Jira and observability, and headless services (Agent SDK, CI) for event-driven agents. See the Evidence sheet. | 2026-11-09 | Executive sponsor | Open
D5 | Lead allocation | Transformation lead fully on the program until Fri 29 Jan 2027; other work paused. | 2026-10-26 | Executive sponsor with the program sponsor | Open
D6 | Value metrics | Adopt the AI code share method and feature-level records; report value metrics with paired quality metrics; team level only. | 2026-11-09 | Executive sponsor | Open
D7 | Expansion teams | Name the 4–5 backend teams and their order in two cohorts (January and February). | 2026-11-23 | Executive sponsor with engineering managers | Open
D8 | Agent compute budget | Monthly envelope per builder set from November telemetry; hard caps on automated runs; reviewed monthly against cost per successful change. | 2026-11-09 | Executive sponsor with finance | Open
D9 | Measurement data access | Read access for the measurement analyst to analytics, Jira, GitHub, deploy logs, incident tool and HR layer and span data. | 2026-10-28 | Executive sponsor | Open
D10 | Production gate for the standard class | Policy gate (auto-promote) once shadow data meets the bar; significant and high-risk keep a human gate. | 2027-05-10 | Executive sponsor with security | Open
D11 | Autonomy ceiling | L3 (opens PRs) by default; L4 only for named runbooks approved by SRE; no L5 in year one. | 2027-06-07 | Executive sponsor with the head of SRE | Open
D12 | Product-builder role | Adopt the role in the career framework with team-level scorecards. | 2027-08-02 | Executive sponsor with HR | Open

## Task force
Task force
Roles first; names to confirm with the people leads (decision D2).
Role | Responsibilities | Allocation | Nominated by | Name | From | Count
Exec sponsor | Biweekly review; decisions; removes blockers. | Biweekly review |  | (name) | 2026-10-26 | 0
Program sponsor | Owns the program with the lead; people and approvals. | About 20% |  | (sponsor) | 2026-10-26 | 0
Transformation lead and AI architect | Plan, framework architecture, standards, bringing teams' efforts into one framework. | 100% |  | Amar Kumar | 2026-10-26 | 1
Framework engineer | Build, test and release the agent framework: skills, subagents, hooks, connectors, evals. | 100% Nov–Jan | Engineering people leads |  | 2026-11-02 | 2
Standardization engineer | 48-repo rollout, scorecard, guardrails, required gates. | 50–100% Nov–Jan | Engineering people leads |  | 2026-11-02 | 2
Measurement analyst | Baseline, AI code share, feature records, dashboards, monthly report. | 50% | Engineering people leads |  | 2026-11-02 | 1
Security champion | Merge the security team's agent; policy packs; access review. | 50% | Security lead | (built the security agent) | 2026-11-02 | 1
Ops/SRE champion | Merge the operations team's agent; incident loop; SRE agent. | 50% | Operations lead | (built the operations agent) | 2026-11-02 | 1
Pilot team lead | Runs the workflow in the pilot team; weekly feedback. | About 20% | Pilot team |  | 2026-10-26 | 0
Product champion | Intent quality and impact thresholds with product owners. | About 20% | Product leadership |  | 2026-11-09 | 0
Core task force members (count) | [5 empty] | 7
Counts members beyond the lead. Target: 6–7. Part-time roles are not counted.

## Agent framework
Agent framework: one marketplace, twelve core agents
Skills-first, packaged as plugins in this repo's marketplace. Existing team agents merge into these components instead of running separately.
Agent or component | Phase | Packaged as | Starts from (this repo) | Existing effort to merge | Target release | Owner
Intent Agent | Plan | Skill + subagent in the plugin | sdlc-core prd-review skill and prd-analyst agent; starter kit /intent | Requirement-analysis agent (part) | v0.5 · Fri 27 Nov 2026 | Framework engineers (TF)
Requirements Agent | Design | Subagent, called from the spec step | sdlc-core prd-review rubric and spec-write skill | Requirement-analysis agent | v0.5 · Fri 27 Nov 2026 | Framework engineers (TF)
Architecture Agent | Design | Subagent | Starter kit architecture-reviewer |  | v1.0 · Fri 18 Dec 2026 | Framework engineers (TF)
Planning Agent | Build | Skill (runs in plan mode) | sdlc-core plan skill; repo-investigator agent |  | v0.5 · Fri 27 Nov 2026 | Framework engineers (TF)
Coding Agent | Build | Claude Code with CLAUDE.md and shared rules | sdlc-core build skill, builder agent, rules/ |  | Available now | Standardization squad (TF)
Test Agent | Test | Subagent | Starter kit test-engineer |  | v1.0 · Fri 18 Dec 2026 | Framework engineers (TF)
Verification Agent | Test | Skill + subagent + Stop hook | sdlc-core verify skill, qa-verifier agent, stop-verify hook |  | v0.5 · Fri 27 Nov 2026 | Framework engineers (TF)
Security Agent | Test / Deploy | Subagent + security policy pack | Starter kit security-reviewer; sdlc-core rules/10-security-and-data | Security team's agent | v1.0 · Fri 18 Dec 2026 | Security champion (TF)
Code Review Agent | Deploy | Subagent + review in the shared CI workflow | sdlc-core pr-reviewer agent and pr-open skill; starter kit review-synthesizer |  | v0.5 · Fri 27 Nov 2026; CI Fri 26 Feb 2027 | Framework engineers (TF)
Release Agent | Deploy | Skill in a CI release job | Starter kit /release-manifest; shared sdlc.yml workflow |  | Fri 26 Mar 2027 | Framework engineers (TF)
SRE Agent | Maintain | Agent SDK service with read-only observability tools | Playbook prompt S1; sdlc-connectors | Operations team's agent | L1–L2 · Fri 26 Mar 2027 | Ops/SRE champion (TF)
Incident Agent | Maintain | Skill | sdlc-core learn and triage skills, knowledge/; starter kit /incident-to-intent |  | v1.0 · Fri 18 Dec 2026 | Ops/SRE champion (TF)
Guardrail hooks | All | Hooks | sdlc-core shell, edit, PR and stop-verify guards; starter kit frozen-test and production-boundary guards |  | Critical repos Fri 18 Dec 2026 | Standardization squad (TF)
Connectors | All | MCP servers | sdlc-connectors (history and schema lookup); Jira, GitHub, observability |  | Jira and GitHub v0.5; observability Jan 2027 | Framework engineers (TF)
Eval harness | All | claude plugin eval + headless claude -p | sdlc-core evals (5 cases, baseline arm); starter kit run_evals.py and EVAL-0001 |  | 15 cases · Fri 18 Dec 2026 | Framework engineers (TF)

## Risks
Risks
Review at every biweekly review. Likelihood and impact: High, Medium, Low.
ID | Risk | Likelihood | Impact | Mitigation | Owner | Status
R1 | Task force members are not freed up, so November targets slip. | Medium | High | Allocation approved by the executive sponsor (D2); checked daily at 11:00; escalated at the next biweekly review. | Program sponsor | Open
R2 | Teams keep building agents on their own, so effort is duplicated and behaviour differs. | High | Medium | One-framework rule (D3); inventory with decisions (1.5); clear contribution path; credit contributors in showcases. | Amar (lead) | Open
R3 | Repo owners are slow to review CLAUDE.md changes, so 40/48 slips. | Medium | High | Claude drafts every change; one-hour review slots; scorecard visible to managers; escalate per team. | Standardization squad (TF) | Open
R4 | Baseline numbers are disputed or missing, so value cannot be shown. | Medium | High | Definitions locked by Fri 6 Nov; team level only; definitions change at most once a quarter. | Measurement analyst (TF) | Open
R5 | Holidays cut capacity (Diwali week in November, year end). | High | Medium | Front-load November; light work 21 Dec – 1 Jan; confirm review dates. | Amar (lead) | Open
R6 | The workflow feels like paperwork, so teams resist. | Medium | High | Tier by change class; agents draft artifacts; measure overhead; delete sections nobody reads. | Amar (lead) | Open
R7 | Human review becomes the bottleneck as AI changes grow. | High | Medium | Multi-agent review in CI; humans judge fit and risk; small PRs; at most 2–3 parallel sessions per builder. | Framework engineers (TF) | Open
R8 | Agents weaken or skip tests to get green. | Medium | High | Frozen tests, test guard hook, independent verifier, eval cases that catch cheating. | Standardization squad (TF) | Open
R9 | Agent sessions reach credentials or production. | Low | High | No production credentials for agents; sandbox and network allowlist; deny rules; access review (7.1). | Security champion (TF) | Open
R10 | A skills-only constraint leaves rules unenforced and event-driven agents unbuilt. | Medium | Medium | Decision D4 with the evidence pack: skills-first plugin with hooks, subagents and connectors; Agent SDK for services. | Amar (lead) | Open
R11 | The lead becomes a single point of failure. | Medium | High | Named owners for every area; a framework deputy among the task force. | Program sponsor | Open
R12 | Metrics get gamed once they become targets. | Medium | Medium | Paired metrics; team level only; read numbers next to retro notes. | Measurement analyst (TF) | Open

## Evidence
Industry evidence: skills, plugins and agents
Vendor facts checked on Fri 23 Oct 2026. Company cases summarise docs/research.md in this repo (re-checked against sources on 22 Oct 2026).
# | What the source shows | Why it matters for our plan | Source
1 | Anthropic packages Claude Code extensions as plugins that bundle skills, subagents, hooks and MCP servers, shared through marketplaces; managed settings can limit builders to approved marketplaces. | Supports 'skills-first, packaged as plugins'. The same plugin also carries the guardrails and connectors we need. | https://code.claude.com/docs/en/plugins
2 | A skill is a folder with a SKILL.md file plus optional scripts and resources; it runs when invoked by name or when the task matches its description. | A skill can run a bundled script, for example one that renders and opens an HTML review page (action 4.3). | https://code.claude.com/docs/en/skills
3 | Hooks run as code before a tool call and can allow, deny or ask. Skills are instructions the model follows. | Rules that must hold (frozen tests, production boundary) need hooks; skills alone cannot enforce them. | https://code.claude.com/docs/en/hooks
4 | OpenAI's Codex documentation describes skills built on the open Agent Skills standard (agentskills.io), available in the Codex CLI, IDE extension and app, with plugins as the way to share them. | Skills and plugins are a cross-vendor pattern, so our investment is portable. | https://developers.openai.com/codex/skills
5 | Gemini CLI extensions bundle a context file (GEMINI.md), MCP servers and custom commands. | Google's coding agent uses the same packaging idea: context, connectors and commands in one installable unit. | https://devops.com/gemini-cli-extensions-bring-customization-to-the-command-line/ (third-party; confirm in the Gemini CLI repository docs)
6 | Google reported on its Q3 2024 earnings call (29 Oct 2024) that more than a quarter of new code is generated by AI and then reviewed and accepted by engineers. | Precedent for reporting AI code share as a company metric, paired with human review. | https://fortune.com/2024/10/30/googles-code-ai-sundar-pichai/
7 | Anthropic's GitHub Action runs Claude Code with plugins in CI (claude-code-action@v1 with plugins and plugin_marketplaces inputs). | The same skills run in PR review and release jobs; no second implementation. | https://code.claude.com/docs/en/github-actions
8 | Claude Code exports OpenTelemetry metrics, including cost, tokens, sessions, lines of code, commits and pull requests. | AI code share and cost per change can be measured from telemetry joined with git. | https://code.claude.com/docs/en/monitoring-usage
9 | Stripe (Minions): unattended one-shot coding agents started from Slack, CLI, web or tickets; pre-warmed devboxes with no production data and no open egress; one set of agent rules shared by every agent tool; more than 1,300 merged PRs a week, all human-reviewed. | Background agents produce reviewed PRs at scale when the sandbox holds no production data, the same idea as our production boundary. | docs/research.md (Stripe row); stripe.dev/blog/minions-stripes-one-shot-end-to-end-coding-agents
10 | Spotify (Honk): built on the Claude Agent SDK; verifiers run in the stop hook and no PR opens if they fail; 1,500+ merged PRs and 60–90% time saved on migrations. Spotify reports agents disabling flaky tests. | Supports our verify gate in the Stop hook, and frozen tests against agents weakening tests. | docs/research.md (Spotify row); engineering.atspotify.com
11 | Ramp (Inspect): a background agent with the full stack and a browser; about 30% of merged PRs within months, later over half; the PR opens with the requester's token so they cannot approve it themselves. | Measure sessions that end in merged PRs; separation of duties at the review gate. | docs/research.md (Ramp row); builders.ramp.com
12 | Uber: uReview covers over 90% of about 65k weekly diffs with 75% of comments rated useful; AutoCover uses a mutation-testing validator to reject weak tests. | Multi-agent PR review at scale works when findings are graded and capped; validate tests, not just count them. | docs/research.md (Uber row); uber.com/blog/ureview
13 | Airbnb: Enzyme to React Testing Library migration of about 3,500 test files in 6 weeks against a 1.5-year estimate, 97% automated. | Migration factories: deterministic steps with an agent step inside, validated by tests. | docs/research.md (Airbnb row); airbnb.tech